## Sheet1
Step | Component | Team
1 | Update Client list in CloudFront Parameter File | DevOps | Hafees to provide
2 | CloudFront CDN - Create CloudFront Distribution | DevOps | 01-Cloudfront.sh
3 | Enable Maintenance Page | DevOps | 02-maint-on.txt | Andreas
4 | RDS Snapshot | DevOps | 03-rds-snap.sh
5 | DynamoDB Backup | DevOps | Shravan
6 | Infrastructure Updates
7 | Deploy Cloudformation Updates
8 | Delete-Stack for Proxy, BI, AIP apps (no data loss will occur) | DevOps | 04-delete-stacks.sh
9 | Static Asset S3 – Create the Static asset website using a S3 bucket | DevOps | 05-static-website.sh
10 | Run the Jenkins job “Deploy aliniq-client-app-web” | DevOps | Shravan
11 | Create-Stack BI, AIP, Proxy, Redis apps | DevOps | 06-create-stacks.sh
12 | Chronos Update-stack | DevOps | 07-update-chronos.sh
13 | DataPipeline Update-Stack | DevOps | 08-update-datapipeline.sh | Test in Dev roll back and update stack
14 | DataProcess-ETL Update-Stack | DevOps | 09-update-etl.sh
15 | DynamoDB Configuration Update-stack | DevOps | 10-update-dynamodb.sh
16 | Post CloundFront Deployment Script - Fix-CDN | DevOps | fix-cdn.py
17 | Post CloundFront Deployment Script - update-hostedzone | DevOps | update-hostedzone.sh
18 | Flyway Schema Update | DevOps | Shravan | 20160323.02
19 | Partition Data Migration and verification | DevOps, Data Team | Documentation to be provided by Data Team
20 | Update RDS Parameters Manually and reboot | DevOps | 11-update-rds.txt / Shravan
21 | Redeploy all Applications, Update AppVersion table | DevOps | Shravan
22 | DevOps Smoke Test-use cdn- hostname | DevOps | DevOps
23 | DNS Configuration | DevOps | 12-final.sh | A record change TBD
24 | Disable Maintenance Page | DevOps | TBD
25 | DevOps / Test Team Smoke Test | DevOps, Testers | DevOps | Hafees & Andreas to settle on hostname to use
Order of Deployments
| EU Prod | 2016-04-01
| US Prod 1 | 2016-04-02
| US Prod 2 | 2016-04-02
| AP Prod | TBD
| Beta US | TBD